## Sheet1
Risk | Description | Severity | Examples | Mitigation Strategy
System Failure | Critical bugs can cause hardware damage or safety hazards | High | Faulty motor control due to unvalidated inputs | Refactor regularly and add validation
Increased Development Time | Every new feature requires workarounds or extra effort | High | New protocol requires rewriting existing stack | Allocate time for debt reduction
Test Coverage Gaps | Inadequate tests cause undetected regressions | High | Memory leak reintroduced due to missing tests | Increase automated tests and code reviews
Loss of Knowledge | Tribal knowledge with no documentation | Medium | Original authors left, code is undocumented | Document thoroughly and onboard new developers
Customer Escalations | Bugs that escape to production impact customer trust | High | Devices freeze after 10 days due to watchdog bug | Improve testing and monitoring
Inability to Reuse | Code is too coupled or hardware-specific to reuse | Medium | Sensor driver hardcoded to specific MCU pins | Modularize and decouple code
Blocked Certification | Product fails compliance due to bad traceability or missing tests | Critical | Failure to meet DO-178C or IEC 61508 guidelines | Maintain traceability and perform compliance audits