## Debt Assessment
Component/Module | Type of Debt | Symptoms | Impact | Evidence | Owner | Date Identified
UART Driver | Code Complexity | Nested conditionals, poor testability | High (delays updates) | Code review, 15% coverage | A. Kumar | 2025-05-10
Bootloader | Update/Process | No rollback, unclear update steps | Critical (risk of bricking) | Bug reports, no version control | S. Mehta | 2025-04-27

## Scorecard
Metric | Threshold | Actual | Risk Level | Notes
Cyclomatic Complexity | ≤ 10 | 17 | High | Refactor needed
Code Coverage | ≥ 80% | 48% | Medium | Increase unit tests
Static Analysis Warnings | ≤ 20 | 113 | High | Use MISRA guidelines
Time to Understand Module | ≤ 1 hr | 3 hrs | Medium | Code readability issue
Bug Reopen Rate | ≤ 5% | 12% | High | Incomplete fixes

## Remediation Plan
Debt Item | Fix Plan | Priority | ETA | Owner | Status
Nested Logic in ISR | Move logic outside ISR, use event queue | High | 2025-06-01 | A. Kumar | In Progress
Legacy Bootloader | Add rollback, write update protocol spec | Critical | 2025-06-15 | S. Mehta | Planned
Missing Tests | Add unit tests for drivers | Medium | 2025-06-10 | R. Das | Not Started

## Review Agenda
Agenda Item | Description
Review Outstanding Debt Items | Walk through top 5 high-impact issues.
Score New Debt | Use the Scorecard Template.
Review Remediation Progress | Update status using Remediation Tracker.
Assign Ownership | Update responsibility matrix.
Log Lessons Learned | Capture recurring patterns.